## Time Recording
Time Recording | [5 empty] | 2016-11-21
Time total: | 1900-01-03 06:30
Date | Start time | End time | Duration | Topic | Description | Keyword
2016-10-04 | 9:00 | 15:00 | 0.25 | Research | Research about blockchains (YT videos, Websites, Papers) | Research
2016-10-05 | 10:00 | 15:00 | 0.20833 | Research | Resaerch about blockchains (YT videos, Websites, Papers) | Research
2016-10-06 | 9:00 | 11:00 | 0.083333 | Research | Research about Ethereum (YT videos, Websites, Papers) | Research
2016-10-06 | 14:00 | 17:00 | 0.125 | Research | Research about blockchains (YT videos, Websites, Papers) | Research
2016-10-07 | 10:00 | 16:00 | 0.25 | Research | Research about Ethereum and IPFS (YT videos, Websites, Papers) smart contracts | Research
2016-10-10 | 10:00 | 11:00 | 0.041667 | Meeting | Weekly meeting: Set up Ethereum Project / How to program a smart contract ? / Research papers | Meeting
2016-10-10 | 11:00 | 13:00 | 0.083333 | Setup | Setting up a blockain, wallet & miners | Setup
2016-10-10 | 14:30 | 17:00 | 0.10417 | Setup | Setting up a blockain, wallet & miners | Setup
2016-10-10 | 9:00 | 17:30 | 0.35417 | Setup | Trying to connect ethereum wallet to the remote blockchain in order to transfer a smart contract | Setup
2016-10-11 | 9:30 | 17:00 | 0.3125 | Setup | Trying to connect mist browser to the remote blockchain in order to transfer a smart contract | Setup
2016-10-12 | 33:30 | 41:00 | 0.3125 | Research | Decentralized document management | Research
2016-10-13 | 57:30 | 65:00 | 0.3125 | Research | Blockchain papers | Research
2016-10-14 | 81:30 | 89:00 | 0.3125 | Setup | Connecting mist client to geth node | Setup
2016-10-17 | 105:30 | 113:00 | 0.3125 |  | Connecting mist client to geth node | Setup
2016-10-17 | 10:00 | 11:00 | 0.041667 | Meeting | Weekly meeting: Set up a private test-net network with 4 nodes / Deploying a smart contract | Meeting
2016-10-17 | 11:00 | 12:30 | 0.0625 | Setup | Research about testRPC | Setup
2016-10-17 | 14:00 | 17:00 | 0.125 | Setup | Setting up 4VMs with testRPC + geth & its dependancies | Setup
2016-10-18 | 11:00 | 12:00 | 0.041667 | Research | Trying to figure out a link between geth & testRPC | Research
2016-10-18 | 13:00 | 17:00 | 0.16667 | Research | Trying to figure out a link between geth & testRPC | Research
2016-10-19 | 9:00 | 12:00 | 0.125 | Setup | Setting up Truffle (for developping smart contract) + Installing Linux on Desktop PC | Setup
2016-10-19 | 14:00 | 17:00 | 0.125 | Setup | Setting up a GIT Repo (Bitbucket, and finally GitHub | Setup
2016-10-20 | 10:30 | 12:30 | 0.083333 | Setup | Setting up Truffle (for developping smart contract) + Mist browser + dependencies (NPM, NodeJS, Electron, Gulp) | Setup
2016-10-21 | 13:30 | 17:30 | 0.16667 | Setup | Deploying contract remotely & locally + geth on 3 nodes | Setup
2016-10-24 | 9:00 | 10:00 | 0.041667 | Setup | Seting up a geth cluster with 3 nodes | Setup
2016-10-24 | 10:00 | 11:00 | 0.041667 | Meeting | Weekly meeting: Set up a geth cluster and define a data structure/scheme for the smart contracts in order to insert inside the blockchain (UUID, identifier, hash values, URN) | Setup
2016-10-24 | 11:00 | 12:30 | 0.0625 | Setup | Seting up a geth cluster with 3 nodes | Setup
2016-10-24 | 14:00 | 17:00 | 0.125 | Setup | Seting up a geth cluster with 3 nodes | Setup
2016-10-25 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  | Time total: | 1900-01-03 06:30
Formulas:
Duration = [End time]-[Start time]
Duration = SUM(D7:[Duration, row above])
Date = DATE(YEAR([Date, row above]),MONTH([Date, row above]),DAY([Date, row above])+1)

## Keywords
Keyword
Administration
Documentation
Meeting
Misc
Organization
Programming
Research
Testing